### Executive Summary

EduSecure is a next-generation, cloud-based Educational Resource Planning (ERP) platform. This update incorporates two mission-critical modules: Parental Oversight Integration and Unified Video Streaming (Live Classroom). By centralizing administrative, pedagogical, and communication workflows—including real-time video—EduSecure removes the need for third-party subscriptions like Zoom or Google Meet, providing a secure, "all-in-one" environment.

### A. Feature List and Task Breakdown

#### 1. Core Infrastructure & Admin (The "Hunter" Approval System)

- Onboarding: Director/Assistant application submission.

- Admin Audit: Review workflow with "Approve/Reject" logic.

- Automated Provisioning: Kafka-triggered email links for school registration.

#### 2. Director & Staff Management

- Role Delegation: Director can assign Assistant and Teacher roles.

- Subscription Logic: Tier-based caps on students, class count, and AI credits.

- Configuration: School-wide branding, grading scales, and secure exam settings.

#### 3. The "EduStream" Video Module (New)

- Integrated Live Lessons: WebRTC-based video streaming (Zoom-like) built directly into the class dashboard.

- Collaborative Tools: Real-time whiteboarding, screen sharing, and "Raise Hand" features.

- Recording Management: Automated storage of lessons linked to the specific class resource feed (Tier-dependent).

#### 4. The Parent Engagement Portal (New)

- Parent Dashboard: View child’s attendance, grades, and schedule.

- Real-time Notifications: Kafka-driven alerts for student exam performance or behavior notes.

- Direct Messaging: Secure channel between Parents and Teachers.

#### 5. Academic Modules (Teacher & Student)

- Resource Feed: Uploading documents, videos, and AI-generated study guides.

- Secure Exam Engine: Parallel, proctored examinations for entire cohorts.

- EduPlay: Interactive Kahoot-style quizzes for engagement.

### B. Work Breakdown Structure (WBS)

1.0 EDU-SPHERE PLATFORM

- 1.1 Requirements & UX Design

  - 1.1.1 Responsive UI Design (React)

  - 1.1.2 Database Schema Design (Oracle 19c)

- 1.2 Backend Microservices (Java Spring Boot)

  - 1.2.1 Identity & Access Service (IAM/OAuth2)

  - 1.2.2 Application & Approval Workflow

  - 1.2.3 Subscription & Tier Management Service

- 1.3 EduSecure Integration (Video/Collaboration)

  - 1.3.1 WebRTC / Media Server Setup

  - 1.3.2 Recording & Transcoding Pipeline (Kafka-based)

- 1.4 Stakeholder Dashboards

  - 1.4.1 Director/Teacher/Student Views

  - 1.4.2 Parental Monitoring Module

- 1.5 Engagement & Examination

  - 1.5.1 Secure Exam Engine

  - 1.5.2 AI Assistant Integration

  - 1.5.3 Gamification (EduPlay)

- 1.6 QA, Security & Deployment

  - 1.6.1 Penetration Testing (Security Audit)

  - 1.6.2 Load Testing (High-concurrency streaming)

### C. PERT & CPM Chart (Critical Path Analysis)

#### Critical Path Method (CPM)

The integration of live video significantly impacts the critical path due to its technical complexity.

- T1: Auth & Security Setup (3 weeks)

- T2: Director Onboarding & Approval Service (3 weeks)

- T3: Core Academic Service (Classes/Students) (4 weeks)

- T4: EduSecure Video Engine Development (6 weeks) — CRITICAL TASK

- T5: Parent Dashboard & Kafka Notification Service (3 weeks)

- T6: Final Integration & UAT (3 weeks)

Total Critical Path Duration: 22 Weeks.

#### PERT Weighted Estimates

| Task | Optimistic | Most Likely | Pessimistic | Expected Time |
| --- | --- | --- | --- | --- |
| Video Streaming Setup | 4 wks | 6 wks | 10 wks | 6.3 wks |
| Secure Exam Logic | 2 wks | 4 wks | 6 wks | 4 wks |
| Kafka Alert Engine | 1 wk | 2 wks | 3 wks | 2 wks |

### D. Gantt Chart (6-Month Implementation Roadmap)

| Month | M1 | M2 | M3 | M4 | M5 | M6 |
| --- | --- | --- | --- | --- | --- | --- |
| Architecture & DB Design | [XXXX] |  |  |  |  |  |
| Onboarding & Approval Flow |  | [XXXX] |  |  |  |  |
| Teacher & Student Modules |  | [XXXX] | [XXXX] |  |  |  |
| EduSecure (Video) Engine |  |  | [XXXX] | [XXXX] |  |  |
| Parent Portal & Kafka Alerts |  |  |  | [XXXX] | [XXXX] |  |
| AI & Exam Engine |  |  |  |  | [XXXX] |  |
| Beta Testing & QA |  |  |  |  |  | [XXXX] |
| Go-Live |  |  |  |  |  | [XXXX] |

### Technical Architecture

- Frontend: React.js with Socket.io for real-time notifications and WebRTC for video.

- Backend: Java (Spring Boot) Microservices architecture for high scalability.

- Event Broker: Apache Kafka to handle notifications for parents, registration link delivery, and processing video recordings.

- Database: Oracle DB (Relational data like grades, attendance, and users) + Redis (for session management and video signaling).

- Video Infrastructure: Jitsi Videobridge or Mediasoup (integrated into our Java backend) for the Zoom-like experience.

- Security: OAuth2 + JWT; Secure Exam Browser protocol integration; AES-256 encryption for all parent-student data.

- AI: OpenAI API integration tailored by subscription tier (Director can enable/disable for specific teachers/students).